## Sheet1
| Media+design | Technical | Orientation
2022-08-31 |  |  | Introduction to project hatchery | Group task
2022-09-07 |  |  | Individual orientation task | 1 hatchery circle
2022-09-14 |  |  | Team orientation task | Zoom info
2022-09-21 | Today | Today | Making the schedule
2022-09-28 | Test posts + layouts for tests | CSS root file | Presentation - Esa and Ira/project plan
2022-10-05 | Posting first advertisements/Show poster draft | Html pages for tests | Submit project plan | 2. hatchery circle
2022-10-12 | 3 more advertisments / Poster final version | JS implementation | Submit poster
2022-10-19
2022-10-26 | POSTER PRESENTATION / ADVERTISEMENT PRESENTATION | TECHNICAL PRESENTATION
2022-11-02 | Making posts | Wordpress implementation |  | 3. hatchery circle
2022-11-09 | Posting posts/feedback | Wordpress implementation
2022-11-16 | Posting posts/feedback | Testing
2022-11-23 | Final presentation | Final presentation
2022-11-30 | Active instagram, facebook and linkedin accounts with advertisments | Wordpress any other framework test plugin | Final presentation presenting
2022-12-07 | Final report | Final report | Final report | Final reflection