## Sheet1
| Media | Design | Technical | Orientation
2022-08-31 |  |  |  | Introduction to project hatchery | Group task
2022-09-07 |  |  |  | Individual orientation task | 1 hatchery circle
2022-09-14 |  |  |  | Team orientation task | Zoom info
2022-09-21 |  |  |  | Making the schedule
2022-09-28 | Test posts - done but not up to our standarts | layouts for tests - one more layout (dragabble) + no test posts | CSS root file - finish css | Presentation - Esa and Ira/project plan
2022-10-05 | Posting first advertisements | Show poster draft | Html pages for tests - It's ok but we should test out it a little more | Submit project plan | 2. hatchery circle | Trying to contact Mari again | Mari said that everything is WIP - meeting at 26.10.!!!
2022-10-12 | 3 more advertisments | Poster final version | JS implementation - add question JS??? Question generation test - finished - what is deployment platform? | Submit poster
2022-10-19
2022-10-26 | ADVERTISEMENT PRESENTATION | POSTER PRESENTATION | TECHNICAL PRESENTATION | Meeting Mari 3041 - 14:15-15:30
2022-11-02 |  | Making posts | Wordpress implementation |  | 3. hatchery circle
2022-11-09 |  | Posting posts/feedback | Wordpress implementation
2022-11-16 |  | Posting posts/feedback | Testing
2022-11-23 |  | Final presentation | Final presentation
2022-11-30 |  | Active instagram, facebook and linkedin accounts with advertisments | Wordpress any other framework test plugin | Final presentation presenting
2022-12-07 |  | Final report | Final report | Final report | Final reflection