## Sheet1
| Media | Design | Technical | Orientation
2022-08-31 |  |  |  | Introduction to project hatchery | Group task
2022-09-07 |  |  |  | Individual orientation task | 1 hatchery circle
2022-09-14 |  |  |  | Team orientation task | Zoom info
2022-09-21 |  |  |  | Making the schedule
2022-09-28 | Test posts - done but not up to our standarts | layouts for tests - one more layout (dragabble) + no test posts | CSS root file - finish css | Presentation - Esa and Ira/project plan
2022-10-05 | Posting first advertisements | Show poster draft | Html pages for tests - It's ok but we should test out it a little more | Submit project plan | 2. hatchery circle | Trying to contact Mari again | Mari said that everything is WIP - meeting at 26.10.!!!
2022-10-12 | 3 more advertisments | Poster final version | JS implementation - add question JS??? Question generation test - finished - what is deployment platform? | Submit poster
2022-10-19
2022-10-26 | ADVERTISEMENT PRESENTATION | POSTER PRESENTATION | TECHNICAL PRESENTATION | Meeting Mari 3041 - 14:15-15:30
2022-11-02 | Progress presentation teaser posts min 3 posts | Making posts | Wordpress research - how to implement data presentation |  | 3. hatchery circle
2022-11-09 | Teaser posts - over the top - catches eye | Posting posts/feedback | Database implementation
2022-11-16 | Explain - what are the 5 competencies | Posting posts/feedback | Admin pages and test pages | Start creating report and presentation
2022-11-23 | Explain what is sincoe | Final presentation - prepare presentation, focus on success, Leo and Marmik | Testing
2022-11-30 |  | Active instagram, facebook and linkedin accounts with advertisments | Delivery | Final presentation presenting
2022-12-07 | Hype it up - even more - countdown | Final report | Final report | Final report | Final reflection